## Slide 1
ANERVEA
Nexus
NEX Sprint 2 CLOSURE · NEX Sprint 3 KICKOFF
NEX Sprint 2: 2026-06-30 – 2026-07-07
NEX Sprint 3: 2026-07-07 – 2026-07-14
COMPLETED
197
NEX Sprint 2
CARRY-OVER
154
into NEX Sprint 3
NEW WORK
47
NEX Sprint 3
PROJECTS
1
covered
CONFIDENTIAL · 09 JULY 2026

## Slide 2
SPRINT OVERVIEW
NEX Sprint 2 — Closure at a Glance
TICKETS COMPLETED
197
NEX Sprint 2
CARRY-OVER
154
into NEX Sprint 3
NEW SPRINT WORK
47
NEX Sprint 3
PROJECTS COVERED
NEXUS
197
tickets
NOTE Team velocity: 197 tickets closed in NEX Sprint 2. 154 carry-overs into NEX Sprint 3.

## Slide 3
197 TICKETS · 1 PROJECT(S)
NEX Sprint 2 — Completed Work by Project
NEXUS
197
100.0% of sprint

## Slide 4
SPRINT KICKOFF
NEX Sprint 3 — Committed Work (395 tickets)
STORIES
341
tickets
TASKS
6
tickets
BUGS
45
tickets
OTHER
3
tickets

## Slide 5
TEAM · ASSIGNEE BREAKDOWN
Team Performance — NEX Sprint 2
TOP CONTRIBUTOR Allen Mathew Cordero · 16 completed of 25
# | Engineer | Tickets | Completed | % Total
1 | Allen Mathew Cordero | 25 | 16 | 6.9%
2 | Deinielle Cruz | 15 | 6 | 4.2%
3 | Dan Rudolf | 11 | 10 | 3.1%
4 | Shane Michael Singwa | 11 | 3 | 3.1%
5 | Dan Denver De Leon | 2 | 1 | 0.6%

## Slide 6
TEAM · TICKET BREAKDOWN
Ticket Breakdown
Team Member | Assigned | Completed | Incomplete
Allen Mathew Cordero | 25 | 16 | 9
Deinielle Cruz | 15 | 6 | 9
Dan Rudolf | 11 | 10 | 1
Shane Michael Singwa | 11 | 3 | 8
Dan Denver De Leon | 2 | 1 | 1
TOTAL | 64 | 36 | 28
TOTAL ASSIGNED
64
TOTAL COMPLETED
36
TOTAL INCOMPLETE
28
COMPLETION RATE
56.2%

## Slide 7
SPRINT CLOSURE
NEX Sprint 2 — Key Achievements
TICKETS COMPLETED
197
NEX Sprint 2
PROJECTS COVERED
1
Nexus
COMPLETION
54.7%
of the sprint
• Hardened the Publications data pipeline — aligned PubMed/bioRxiv/Crossref queries to EuropePMC scoping and eliminated the bioRxiv drug-in-title matcher's ~99% false-positive rate, while fixing the journal/KOL classification flags and abstract/mesh-term coverage gaps.
• Restored KOL pipeline integrity — root-caused the 2026-06-22 nulled-matches regression, onboarded 5 previously inactive sources, and cleaned investigator name normalization.
• Cleaned entity and scope data across signals — de-contaminated the drug and gene/biomarker lists, corrected therapy-area source mapping, and shipped a shared rule-based noise-filtering tagger plus the signal-generator reference skill.
• Delivered Collector Intelligence table views end to end — table infrastructure, per-tab implementations, paginated export endpoints, and the Indication Registry overview with prefetch/navigation performance wins.
• Standardized the front-end design system — unified design tokens, page-shell components, dialogs, and cards/list items for a consistent UI.
• Shipped signals-read and list APIs for AlfaKinetic — a per-client x-api-key signals endpoint over the indication signal tables plus the indication/KOL/product/conference list endpoints.
• Improved test and collector reliability — fixed a time-bomb flaky test and evaluated the scrapling library for web-scraping collectors.

## Slide 8
RISKS & BLOCKERS
Roadblocks and Next Steps
R01
Publications work blocked
Impact: NEX-173 (pub_07) is blocked, stalling part of the publications collector track.
Mitigation: Resolve the upstream dependency and confirm requirements before it slips a second sprint.
Help needed: Data/product owner to clarify scope and unblock the dependency.
R02
High carry-over into Sprint 3
Impact: 154 tickets carried over against 197 completed (~55% completion); Sprint 3 opens at 395 committed, risking a compounding backlog.
Mitigation: Triage carry-over on day one, descope non-critical items, and cap WIP per engineer.
Help needed: Product to re-prioritize and formally descope the Sprint 3 commitment.
R03
Work and completion concentrated unevenly
Impact: Most pipeline delivery sat with one engineer while others closed 3/11 and 6/15 of their tickets — a bottleneck and bus-factor risk.
Mitigation: Rebalance assignments, pair on stuck tickets, and spread pipeline knowledge.
Help needed: Leadership input on staffing and load balancing.

## Slide 9
ANERVEA
Engineering Leadership
DISTRIBUTION
Engineering Team · Product Lead · CTO · QA · DevOps
Generated from Jira · 09 July 2026 · Confidential — not for external distribution